## Marking
Sprint Planning Meeting Evaluation Template
GitSudo
Craig MacLeod, Kent Power, Liam Elliot
Product Backlog Grooming
Grade Item | Points | Rubric | Notes
Discussed whether new stories need to be added | 1 | Yes = 1; No = 0 | We decided that no more stories are needed for this sprint.
Discussed existing rankings and modified if necessary | 1 | Yes = 1; No = 0 | No tasks required modification. May need to change rankings.
Discussed any stories that can be split (high-priority user stories that are too large for a single sprint MUST be split) | 1 | Yes/NA = 1; No = 0 | No user stories needed to be split, they should be doable in this sprint.
Reviewed every existing user story for the following: - Is it still relevant, or should it be cancelled? - Should the description be updated? - Are the story points still accurate? | 3 | All stories, all questions = 3 Most stories and/or most questions = 2 Some stories and/or some questions = 1 Not reviewed = 0 | All stories still relevant, may need to update some descriptions, the story points were all still relative.
Grooming meeting is completed within time box | 1 | Yes = 1; No = 0
Total | 7
Sprint Planning
Grade Item | Points | Rubric | Notes
Correct user stories are selected, based on rank and size | 2 | Always = 2 Some lower priority stories out of order = 1 Highest priority story not added = 0
Generated all tasks for a story before grooming (i.e. no ideas are omitted/shot down) | 1 | Yes = 1; No = 0
For each proposed task:
1) Is it necessary, or can it be deleted/merged with another task? | 0 | Most/all tasks = 1 Some/no tasks = 0 | One task was merged.
2) What is the estimated effort? | 1 | All tasks = 1 Most, some or no tasks = 0 | all sprint 2 tasks should be doable.
3) Who volunteers to own the effort? | 1 | All tasks = 1 Most, some or no tasks = 0
Upon completion, the scope of the sprint is appropriate in terms of velocity and estimated hours | 1 | about 70% - 130% of hours, 50% to 200% of velocity = 1 Outside target range = 0 | it is appropriate and can be done.
Planning meeting is completed within time box | 1 | Yes = 1; No = 0
Total | 7

## Scrum Master Cheat Sheet
Planning Meeting Cheat Sheet
Backlog Grooming
1) State the purpose of the meeting (backlog grooming and sprint planning)
2) State the timebox for the backlog grooming meeting
3) Ask whether new user stories need to be added to the backlog
4) Identify any large user stories that can be split
5) Ensure that no user story that might be in-scope within the next two sprints is too large to fit into a single sprint, based on average velocity. Such user stories MUST be split.
6) Review the entire list of user stories (excluding completed stories) and ask the following questions:
a) Is this story still relevant, or should it be cancelled?
b) Does the description need to be updated?
c) Are the story points still accurate?
7) Clearly state that the grooming meeting is over and the planning meeting has started
Sprint Planning
8) Select the next highest ranked user story that can fit in this sprint and add it to the sprint (may not necessarily be the highest ranked, if higher ranked stories are too large but lower ranked ones still fit)
9) Brainstorm and record all tasks that may potentially be required to implement the user story. No ideas should be rejected and tasks with significant overlap are acceptable at this point.
10) When no more tasks can be thought of, review the list of tasks for the following:
a) Is the task necessary, or can it be deleted or merged with another story?
b) What is the estimate for this task?
c) Which team member volunteers to own the effort?
11) Based on story points and hours, can your group take on more work this sprint? If yes, return to step 8. If no, go to step 12.
12) End the meeting.